ENTERPRISING PROJECTS:

A PRACTICAL GUIDE FOR TEACHERS

Enterprising projects allow students to develop enterprise capacities by taking on a significant degree of project ownership. Teachers can facilitate enterprise learning by providing a sound structure that follows a systematic process of design.

Steps 1 to 3 below provide a practical guide for teachers who are facilitating enterprising projects.

- Explore and define the task

a) Checklist of key roles for the teacher/facilitator

- support students to explore an area of need within the wider community

- facilitate access to businesses and/or community organisations that will provide the need or purpose to be addressed by the project

- encourage students to engage in project planning and take responsibility for project management

- as a result of the exploration, support students to negotiate a defined brief for their project

- ensure that the project brief addresses the needs of those beyond the immediate classroom by producing an outcome  for an identified user or client

b) Questions to assist students to explore and define the task

The need or opportunity

- Is there a product, a system or an environment that is not doing its job effectively?

- Can we think of ways to do it better? (Cheaper, stronger, more attractive etc)

- Is there something we can use in a new way or for a different purpose?

- Is there a need that has no practical solution?

The user

- Who will use the design?

- How will they use the design?

- What will the design have to do to meet the users’ requirements?

- What qualities (aesthetic) will the design need for the user to appreciate it?

The client

- Who has requested the design? Why?

- What will the design have to do to meet the client’s requirements? (functional and aesthetic)

Resources

- What is the budget?

- How much time is available?

- What other resources are available? (Skilled people, information, materials, processes, equipment etc)

Social and environmental considerations

- Who else might the design affect? How?

- Is there an environmental impact?

- Are there laws, rules or regulations that you need to consider?

Criteria for success

- What will the design have to do to be successful?

- What are the most essential success-criteria and which are desirable?

- What is the priority order for the success-criteria?

Defining the task

- How can we bring all these considerations together into a clear and concise statement of the design task or design brief?

c) Tips for teacher / facilitators

The following advice was provided by teachers who completed the Building Bridges Project with their classes. The advice is drawn from teachers’ written suggestions and from comments that were made orally.

Choosing engaging and authentic tasks/negotiating tasks with students

- It is important to provide open briefs but set clear limits to the project – available expertise, time, budget, etc. The task must allow students to be enterprising, think creatively and use their initiative but at the same time it must be specific enough to allow the teacher to plan activities and provide support.

- I had to teach my students about the design process. We used the process to plan and manage what the students did.

- We needed a long planning time. And enough lead time to allow students to properly negotiate an authentic task – something that was relevant to the real world.

- It was important that we linked the task to a need or want that was meaningful to the students. It helps when the project is related to something beyond the classroom. My students were keen to improve something for other people. Dealing with ‘real needs’ made the project authentic.

- Because the project was authentic, students had a great deal of ownership. Kids must be interested in the brief and they must have fun.

Establishing partnerships with the community to support design tasks

  - A personal approach was important for our initial communication. It was essential to let the business know how it might benefit from an involvement.

  - When dealing with an outside organisation we found that we had to hold regular meetings – to make sure that their people knew how the project was progressing and to ensure clear communication.

  - We found that people in the community were willing to provide great assistance but we had to negotiate practical arrangements and accept that sometimes we had to compromise.

  - Don’t push too hard. We knew that we were not a part of the organisation’s core business.

  - We had to state exactly what we needed  – and our community experts needed to know the objectives of the project.

Helping students to evaluate needs and opportunities

- We went back to past projects and talked about how peoples’ needs were considered.

- We challenged our students to identify problems in the community, the home or the school. We had lots of discussion about opportunities to improve things. Then we did some evaluation – surveyed potential users to check that we had assessed the need correctly.

- We talked about the idea of being enterprising – using our brains and eyes to see what needed doing. Students worked in groups to record their ideas about people’s needs.  When we had some suggestions, we surveyed people to see whether there was really a need to improve something.

- Generate and develop ideas in response to a defined brief

a) Checklist of key roles for the teacher/facilitator

- facilitate access to outside experts or those with relevant vocational skills to support project development

- facilitate ongoing student partnerships with businesses and/or community organisations to develop and resolve the project

- support students’ capacity to relate project processes and activities to ‘real world’ processes and activities

- encourage recognition and feedback for students from those whose needs are being met by the project.

- support students capacity to accept responsibility for evaluating and modifying ideas

b) Questions to assist students to generate and develop ideas in response to a
     defined brief

Generating ideas

- What design solutions exist that address similar needs, problems or opportunities?

- What are the advantages and disadvantages of these solutions?

- What creative thinking techniques can we use to generate new ideas?

- What ideas can we come up with?

Representing ideas

- What techniques can we use to represent my ideas (sketching, story-boarding, drawing, modeling, flow-charts, diagrams etc)?

- Who is the audience (me or others) and what is the purpose of the representations (rough ideas, resolving ideas, presenting ideas etc?)

- Which techniques can we use to represent ideas as they become more resolved?

- How can we improve skills in representing ideas?

Investigating resources

- What materials/processes/equipment/etc could be used for the design?

- What resources are available?

- What are the performance properties the design requires?

- What risks (safety, cost, environmental) are associated with using the materials/processes/equipment/etc?

- How can we test the suitability of the materials/processes/equipment?

- How can we improve my skills in using the materials/processes/equipment/etc proficiently and safely?

- If we are can’t use the materials/processes/equipment/etc, can someone else help?

- Which materials/processes/equipment/etc will we choose and how do they relate to the success criteria?

Resolving ideas

- What are the advantages and disadvantages of each idea in relation to the success criteria?

- Have we considered the long-term (social and environmental impact) as well as the short-term (money, time, appearance) consequences of the design?

- What do the client and user think?

- What design idea/s will we choose and why?

- Will the chosen design meet the success criteria? (essential? desirable?)

- Do we need any further modifications to the design?

Finalising the proposal

- Do we know exactly what is involved in producing the design?

- Do we need to further detail the design? (technical construction drawings, pattern pieces, layout, storyboarding, flowcharts, models)

- Which equipment and material is required?

- How much will it cost?

- What is the step-by-step sequence that will need to occur to produce the design?

- Do we have the skills needed to do each step or will we need more time to practice?

- How long is each step likely to take?

- Who is responsible for each step?

- Does our proposed time plan and budget meet the success criteria?

- Will modifications be required?

Managing safety risks

- What safety risks can we identify? (user capability and behaviour, materials, equipment, facility, teacher expertise)

- Where can we find sound advice?

- How can we eliminate or control the risks?

- If the risks cannot be controlled how will we modify the design?

Managing production

- Have the necessary information, materials and equipment been acquired?

- Is the equipment set up safely and working effectively?

- How and who will manage storage and equipment maintenance issues?

- Do we need particular skills to be modelled (demonstrated) or reviewed with us or are we able to proceed independently?

- Do we need an expert to supervise our work?

- Is the production proceeding according to time plan and budget?

- Is the quality of production work appropriate to the success-criteria?

- What modifications do we need to make to the planned design and production?

c) Tips for teacher / facilitators

The following advice was provided by teachers who completed the Building Bridges Project with their classes. The advice is drawn from teachers’ written suggestions and from comments that were made orally.

Helping students to generate ideas

- Our students came up with some fairly general ideas using a mind map. Then, they worked co-operatively in teams to further develop some concepts. We evaluated each concept – we rated them using our criteria (for success).

- We teach our students thinking skills – concept maps, brainstorming, pmi’s (plus, minus and interesting).

- Our students researched solutions to similar needs – and they evaluated how well others had resolved the problem.”

- We found that we had to give our students time to think, negotiate and compromise – particularly working closely with our outside partners to see what is practical.

- It was really important to give kids time to work through their own ideas and suggestions.

- Produce and evaluate a practical outcome recognising the consequences of their decisions

a) Checklist of key roles for the teacher/facilitator

- ensure that project results are developed from ideas that are generated by students

- evaluate students capacity to appreciate reasons for the sequence of project activities undertaken during the project

- support students capacity to describe their own learning in relation to a wide menu of enterprise capabilities

b) Questions to assist students to produce and evaluate a practical outcome
     recognising the consequences of their decisions

Design Solution

- What did we produce as a result of the design process?

- Does it work for the client and user? Do they like it?

- In what ways did our design solution achieve each success-criteria?

- What aspects of the design solution did not achieve the success criteria?

- How would we do it differently next time?

Design Process

- What was the design process we used?

- How could the design process be improved?

- Was our documentation processes helpful? Why or why not?

- Did we meet the requirements of the design task? Why or why not?

- What skills did I gain or further develop?

- Did the group work well as a team?

Learning outcomes

- What enterprising capacities have I developed?

- Which syllabus outcomes were we focusing on?

- How well have I progressed towards achieving each outcome?

- What experiences do I need to improve in my progress?

c) Tips for teacher / facilitators

The following advice was provided by teachers who completed the Building Bridges Project with their classes. The advice is drawn from teachers’ written suggestions and from comments that were made orally.

Helping students to produce quality solutions

- We found that we had to give our students time to think, negotiate and compromise. We had to work closely with our outside partners to see what was practical.

- The class reviewed examples of the design process and discussed what each step is about and why it is important.

- Students worked towards the criteria (for success). Always checking quality against the criteria.

- It was important that the students learnt making skills. When necessary, community people provided help … We had to provide freedom and time for students to develop skills. Once they did this quality was not a problem.

- It was really important to give kids time to work through their own ideas and suggestions.

- I encouraged students to share their ideas with their peers. And they had to be prepared to question other people’s ideas.

- Goal setting was important. We taught students about the importance of management – we established timelines and set time limits.

- It was important that students understood that the project was part is of the mainstream Technology program and that their learning would be assessed and reported.